REQUEST FOR QUOTATION FOR THE SUPPLY OF EXTERNAL AUDITING SERVICE EXTERNAL AUDIT OF GOAL SOUTH SUDAN FOR 2016

GOAL is an International humanitarian agency dedicated to alleviating the suffering of the poorest of the poor for over thirty years GOAL has responded to natural and manmade disasters in the developing world implementing relief, rehabilitation in ten developing countries and has been working in South Sudan since 1985.

Scope of work:

GOAL, South Sudan is seeking to appoint auditors for the following purposes:

To audit GOAL South Sudan financial statements which will be part of GOAL Group audit for which Deloitte, Dublin will be the lead auditors. This part will be conducted based on the brief provided by GOAL, Dublin; it will be made available to the auditors prior to their commencement of the assignment.

- Audit the Financial statements of GOAL, South Sudan

- Verification of closing cash balance and stock as on 31.12.2016

- Checking of authenticity of vouchers and basis for an appropriate sample of transactions during 2016 as per the books of accounts.

- Verifying the entries thereof into the correct account heads and rectification if any material discrepancy arise thereof.

- Verifying of journal entries ensuring adherence to satisfactory accounting system in relation to accrual basis.

- Recommend necessary entries to this effect if material

- Verification of Fixed assets and depreciation schedule.

- Verification of necessary reports of financial statements including notes to financial statements from the books of accounts (Tally and SAGE) in the format as suggested by GOAL, Dublin. i.e. in Euro.

- Verifying the correctness and authenticity of financial statements in the format as suggested by Dublin.

- Issue of Management letter.

Timeline:

. The projected timeline is as follows:  This can be discussed further at the briefing meeting.

| Activities | Time |
| --- | --- |
| Verification of Closing Cash Balance ,Stock and Donation in Kind on 31.12.2016 | 31.12.2016 |
| Audit Commencement | 01.11.2016 |
| Checking of vouchers verification of entry to correct account heads | 01.11.2016 to 31.01.2017 |
| Verification of journal entry and recommending the rectification entries | 01.11.2016 to 15.02.2017 |
| Verification of depreciation schedule | 01.01. to 31.01.2017 |
| Verification of necessary reports of financial statements, correctness of the statements and its verifications | 15.02.2017 |
| Review meeting | 03.02.2017 |
| Resolution of outstanding issues | 08.02.2017 |
| Sending draft report to HQ | 09.02.2017 |
| Signing off financial statements by FC & CD | 24.03.2017 |
| Signing off financial statement by Auditor | 24.03.2017 |
| Issue of Management letter and issue of audit deliverables | 24.03.2017 |

Process to be undertaken and GSS expectations:

Once the audit is formally commissioned, the Audit representative will meet the GSS finance team to brief them regarding the timeframe and their requirements in relation to all documentation and access to information.

GSS in turn will ensure all requested information and documentation is readily available.

Audit firm will ensure that a team of experienced staff, preferably with NGO audit experience, will undertake the assignment.

It is expected that the entire audit team will be briefed about GOAL and its work in South Sudan prior to undertaking the assignment.  In case any briefing from GOAL is required in this regard, this should be requested prior to the audit.

As GOAL South Sudan finance is extremely busy it is important that the audit team is aware of the following:

- All documentation, information required to facilitate the audit will be made available however prior notification is required.

- The GOAL South Sudan Finance team will facilitate the auditors as best they can.  However, in light of GOAL’s ongoing work commitments, the finance team will appreciate if all queries and/or clarifications are sought based on the timeframe agreed during the briefing meeting, and that all information requirements are notified well in advance.  This will facilitate both GOAL and the auditors to meet their respective agendas.

- Access to GSS office is restricted to working hours 9:30 am to 5:30 pm (This may change in light of security protocols)

- GSS office is not accessible on weekends or holidays as per the attached schedule.

On completion of the audit a review meeting will be held at the GSS office with the audit representative and the GSS finance team together with the Country Director if necessary

All copies of the reports as submitted to Dublin will be shared with GSS.

Requirements

- Registered auditors, with a network of international branches or affiliates

- Registered auditors should be based in Juba to allow for a smooth and efficient audit procedure

- Sufficient staff of the required calibre to ensure a quality audit is carried out within the desired timeframe

- Demonstrable experience leading a group audit, where component audits are carried out by auditors not linked to the lead auditor

- Experience auditing large international or national charitable organisations

- A proposed audit plan and fee proposal expressed in Euro, USD or GBP

- Provide 2 relevant references

Evaluation Criteria

- Response to the TOR; Approach, methodology and work plan

- Qualifications of proposed Auditors

- Evidence of past experience; at least 2 references

- Cost

Timeframe

The field audits must be complete by 31st March.

Tenders should be submitted to tjohn@ss.goal.ie  cc   lfoster@ss.goal.ie not later than 5.30pm on 25th of October 2016.

Enquiries or requests for further information should be addressed to the same email address.