Terms of Reference (TOR) for

Final Performance Evaluation of the project ‘Humanitarian Outreach for Protection and Empowerment (HOPE)’

February 2026

Table of Contents

1.	Who is the Danish Refugee Council?	2

2.	Purpose of the consultancy	2

3.	Background	2

4.	Objective of the consultancy	3

5.	Scope of work and Methodology	5

6.	Deliverables	6

7.	Duration, timeline, and payment	7

8.	Proposed Composition of Team	8

9. Eligibility, qualification, and experience required	8

10. Technical supervision	9

11. Location and support	9

12. Travel	10

13. Duty of Care	10

14. Submission process	10

15. Evaluation of bids	10

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

DRC has been operational in South Sudan since 2005, implementing multi-sectoral responses including Protection, Camp Coordination and Camp Management (CCCM), Economic Recovery, Shelter and Non-Food Items (SNFI), WASH, Humanitarian Disarmament and Peacebuilding (HDP). DRC is implementing projects in Upper Nile, Abyei Administrative Area, Eastern Equatorial States and countrywide through mobile response teams.

# Purpose of the consultancy

The Danish Refugee Council (DRC) South Sudan invites qualified consultants to submit technical and financial proposals to conduct a Final Performance Evaluation of the project, incorporating a Knowledge, Attitudes and Practices (KAP) survey component on Water, Sanitation and Hygiene (WASH).

The purpose of this consultancy is to comprehensively assess the overall performance and results of the project, including its effectiveness, efficiency, relevance, and coverage. The evaluation will examine the extent to which the project has achieved its intended objectives and key results, and will analyse performance at output, outcome, and impact levels in line with the project’s logical framework.

In addition, the consultancy will assess the current status of key Water, Sanitation and Hygiene (WASH) outcome indicators through a KAP survey. This will provide an in-depth understanding of behavioural changes associated with hygiene promotion activities implemented in the project areas, evaluate their effectiveness, and generate evidence-based lessons learned and recommendations to inform ongoing and future programming.

# Background

DRC is currently implementing a 15-months US government funded project ‘Humanitarian Outreach for Protection and Empowerment (HOPE)’ (January 1st, 2025, to March 31, 2026). The project locations include Upper Nile (Malakal, Fashoda and Manyo Counties); Unity (Rubkona, Mayom, Koch and Guit Counties); and Abyei Administrative Area (Rumameer, Amenth-Aguok, Alal, Abyei Town Counties) as well as different counties countrywide based on the Mobile Response Team interventions. The primary focus of this project is on Protection, Shelter and Settlement, WASH and Humanitarian Coordination, Information Management, and Assessment (HCIMA), with the goal of ensuring that Displacement and conflict-affected individuals and community structures are empowered to foster sustainable protection and equitable decision making, paving the way for lasting positive change and durable solution.

The purpose of the program is the following:

- Improving access to community based comprehensive responsive and remedial protection services for crisis affected communities in hard-to-reach and protection risk priority locations

- Strengthening self-management and leadership capacity within displaced communities to ensure equitable, efficient, and coordinated delivery of humanitarian assistance, while promoting accountable collaboration among community leaders, local government, and humanitarian actors.

- Enhancing safe and dignified living conditions for displaced vulnerable communities through provision of lifesaving shelter and NFI assistance

- Improving equitable access to clean water sources, sanitation, and hygiene to reduce risks of waterborne diseases and gender-based violence in the targeted crisis-affected locations.

Theory of Change (ToC)

The proposed Theory of Change (ToC) states that: If the lifesaving needs of displacement-affected populations are addressed, and if early recovery interventions are supported, and if the political, security and economic environment remain conducive, then the probabilities, severity, and prevalence of protection risks will be reduced, empowering displacement affected communities to be more self-reliant and access transitional pathways out of displacement or vulnerable statuses.

# Objective of the consultancy

The objectives of this Final Performance Evaluation are to:

- Assess the overall achievement of the project objectives and results, including changes in the living conditions, protection environment, and resilience of displacement-affected populations across Protection, Shelter/NFI, WASH, and HCIMA components.

- Evaluate project performance in terms of quality, effectiveness, relevance, and contribution to tangible outcomes at household and community levels.

- Measure endline values of key project indicators, including mandatory outcome indicators, in order to determine the final level of achievement against the project’s logical framework.

- Conduct a comprehensive WASH Knowledge, Attitudes and Practices (KAP) assessment to measure change against the baseline assessment conducted in 2025:

  - Assess community knowledge related to safe water, sanitation, and hygiene practices after the intervention.

  - Identify gaps, misconceptions, and barriers affecting the adoption of recommended WASH behaviours shared during the intervention.

  - Examine perceptions, beliefs, and cultural norms influencing hygiene and sanitation practices.

  - Gauge willingness to adopt improved practices.

  - Observe and document actual behaviours related to water collection, storage, sanitation, and hygiene.

  - Compare reported and observed practices with recommended standards to identify risky behaviours and behavioural gaps.

- Examine the extent of community participation and local ownership in the intervention.

- Document lessons learned, unintended outcomes, and key contextual or operational factors that influenced implementation, performance, and impact, and provide actionable recommendations to inform future programming and advocacy.

Table 2: Mandatory Outcome Indicators to be measured during the Final evaluation

| SN | Indicators |
| --- | --- |
| 1 | Percent of individuals who demonstrate improved psychosocial wellbeing after receiving protection services |
| 2 | Number and percent of humanitarian organizations utilizing information management services |
| 2 | Number and percent of humanitarian organizations directly contributing to information products |
| 3 | Number of products made available by BHA-funded information management services that are accessed by stakeholders |
| 4 | Number and percent of individuals reporting satisfaction with the quality of the NFIs received |
| 5 | % Percent of settlement beneficiaries who believe settlement interventions met or exceeded expectations |
| 6 | Percent of households reporting satisfaction with the contents of the WASH NFIs received through direct distribution (i.e., kits) or vouchers (WASH NFI) |
| 7 | Percent of households reporting satisfaction with the quality of WASH NFIs received through direct distribution (i.e. kits), vouchers, or cash |
| 8 | Number of individuals directly utilizing improved sanitation services provided with BHA funding |
| 9 | Percent of households targeted by the hygiene promotion activity with no evidence of feaces in the living area" |
| 10 | Percent of individuals targeted by the hygiene promotion activity who know at least three (3) of the five (5) critical times to wash hands |

Key Proposed Evaluation Questions based on Evaluation Criteria

Relevance & Coherence

- To what extent were the project objectives and activities aligned with the needs, priorities, and protection risks of displacement-affected populations in the targeted locations?

- How coherent was the HOPE project with national strategies, local priorities, and other humanitarian interventions implemented by DRC and other actors?

- To what extent did the project demonstrate conflict sensitivity and responsiveness to evolving contextual dynamics?

Effectiveness & Coverage

- To what extent did the project achieve its intended outputs and outcomes across Protection, Shelter/NFI, WASH, and HCIMA components, as outlined in the logical framework?

- How effectively did the project reach its intended target populations, including women, men, girls, boys, and persons with disabilities, in hard-to-reach and high-risk areas?

- What factors enabled or constrained the achievement of project results?

Efficiency

- To what extent were project resources (financial, human, and material) used efficiently to achieve planned results?

- How appropriate and timely were the project implementation modalities, including coordination mechanisms and Mobile Response Team interventions?

Impact

- What changes—intended or unintended—can be observed at household and community levels as a result of the project, particularly in relation to protection outcomes, living conditions, and access to basic services?

- To what extent did the project contribute to reduced protection risks and strengthened self-reliance among displacement-affected communities, in line with the Theory of Change?

Sustainability & Localization

- To what extent are the benefits of the project likely to be sustained beyond the project duration?

- How effectively did the project promote community participation, ownership, and leadership, and what role did local actors and community structures play in sustaining results?

# Scope of work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how the objectives of the project will be achieved, and the support required from DRC technical team (MEAL).

Geographic Scope

As highlighted in the background section above, the Final evaluation will be conducted in areas where the project is being implemented, and these include at least; Upper Nile (Malakal, Fashoda and Manyo Counties), and Abyei Administrative Area (Rumameer, Amenth-Aguok, Alal, Abyei Town Counties). This will be conducted between February and March 2026 as detailed in the tentative workplan/implementation timeline.

Methodology

The Final evaluation process will encompass desk review as one of the approaches, analysis of secondary data from various sources which will include but not limited to progress reports, beneficiary data among others. Primary data will be gathered directly from the project beneficiaries through Qualitative and quantitative mixed methods of data collection, including focus group discussions (FGDs), key informant interviews (KIIs), transect walks and observation of project activities.

- Desk Review

At the inception phase, the desk review will include a detailed analysis of key approved project documents, Proposal, MEAL plan, updated Indicator Tracking Table (ITT), Detailed Implementation plan, monthly progress, Interim reports and semi-annual performance reports, Baseline Survey report and other relevant documents. DRC will share these documents with the selected consultant to support the preparation and submission of a comprehensive Inception report which will be shared with DRC for review and appropriate feedback prior to data collection.

- Quantitative Household survey

The consultant will conduct a household survey with a selected representative sample from the targeted locations to gather comparative data on the Protection, Shelter and Settlement, WASH and Humanitarian Coordination, Information Management and Assessment (HCIMA).

- Sample design

The consultant will be required to generate a statistically representative sample from the study population (target counties) to determine the final sample size of respondents or households to be selected for the Final evaluation. The sampling techniques/approach that will be proposed by the consultant should be guided by the context and the existing logistical realities such that quality data is gathered for informed decisions, and this should be clearly detailed on the Technical Proposal and Inception report.

- Qualitative Data Collection Method

After review of the approved project documents, the consultants will expected determine the categories key stakeholders or participants to be interviewed during the qualitative approach for each sectors of intervention and each county targeted with this response.  The consultants will also decide on what qualitative data collection approaches (KII, FGD and others) will be employed to ensure that all important data/information are captured, the data gathered from this approach will be triangulated with that from household survey in order to have an inclusive survey findings/result.

Some of the prospective participants for FGDs will include the male and female beneficiaries in relevant age categories separately. KIIs will include key DRC staff members (Technical Coordinators, Chief of Party, Head of Programme, Grants team, Area Managers, Project Officers, MEAL), local authorities, youth representatives, community leaders, women's representatives, and other relevant stakeholders. However once selected, the consultant will also be required to provide additional details on their qualitative research methods. This will include:

- Identifying specific categories of respondents for each question and a rationale must be provided as to why those respondents were selected;

- Clear justification for selected data collection methods, including criteria for selection of participants for FGDs and KIIs.

# Deliverables

The consultant shall submit the following deliverables, according to the ToR and within the agreed timeline:

- Inception report – outlining the key scope of the work, training manuals, intended Final evaluation questions, detailed methodology and data collection tools, data sources and analysis approach, roles and real time frame, and suggested work plan. The inception report will be submitted to DRC five (5) days after signing the contract. This is to ensure that both the consultant and the DRC team have a common understanding of the assessment.

- Implementation plan – will include the detailed assessment process and timeline with a detailed calendar of key activities and milestones.

- Draft Final evaluation report: the consultant should submit the draft report to DRC according to the recommended structure within the agreed timeline.

- Executive summary

- Brief background (as directly relevant to the report’s analysis and conclusions)

- Methodology (including challenges and data collection approach)

- Key findings and conclusions by sector/result (supported with relevant data and data sources)

- Key best practices with details of how they might be replicated, and recommendations for implementation of future projects and wider learning, by sector.

- Annexes, including a list of all data collection tools, Final evaluation Dataset (in excel or CSV), work schedule, and any other relevant information

The preliminary findings will be presented to DRC through a presentation, giving the opportunity for collective feedback before the final report is produced.

The report will be reviewed to ensure that it meets the required quality criteria. Comments from relevant DRC program staff will be provided within five (5) working days after the submission of the draft report.

- Final report: The consultant will be required to address all comments provided by DRC program staff. The report should be finalized in less than five (5) working days after receiving the revised draft from DRC; however, this timeline can be revised backward depending on the urgency of the work. The consultant should maintain the requirements for the content, format, depth and length, overall quality, and approved timelines. Once finalized, the Final evaluation report will be shared with DRC. DRC will then submit to the donors (US Government representative in South Sudan). The summary results/findings will also then be disseminated in different coordination forums to reach other humanitarian agencies and stakeholders.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be not more than 35 days. The consultant shall be prepared to complete the assignment not later than April 14th, 2026, and below is the detailed description of the activities and tentative timelines.

Budget

The budget allocation for the Final evaluation will cover consultant fees, travel expenses, data collection, analysis tools, and any other relevant costs. The consultant will be required to submit financial proposal for the provision of these services with clear breakdowns. The cost of travel and other expenses should be included in the overall quotation for the service. Agreed rates will be based on prevailing market competitive rates and value for money. The consultant is responsible for the following:

- The consultant will be responsible for payment of any tax or other fees related to this assignment.

- The consultant is responsible for any insurance, including medical and travel, related to this assignment.

- The consultant is responsible for his/her working tools, such as computers, mobile phones, tablets for data collection, etc.

- Payments will be in three installments: 30% after submission of the inception report, 30% after submission of the draft report, and 40% after submission of the final approved report to DRC.

- Please note that a partial payment hold-back will be in effect until a final report has been approved by DRC

# Proposed Composition of Team

- Lead consultant/Team Leader

- Field Research Coordinators

- Data Analyst

- Enumerators

# 9. Eligibility, qualification, and experience required

Eligibility:

- The consultant should have the legal authorisation to work in South Sudan. The consultant should not be blacklisted due to corruption and other issues.

Qualification:

- A postgraduate qualification in Social Sciences, Journalism, Development studies or other related disciplines is also strongly required.

Experience:

- At least 7 years of experience in carrying out both quantitative and qualitative research, and impact measurement. Proven experience in conducting primary data collection, including in fragile/developing contexts.

- Demonstrated experience in conducting spearheading assessments, surveys or evaluations, particularly in humanitarian settings.

- Expertise in protection, livelihoods, and/or camp coordination and management.

- Strong understanding of the South Sudan context, the humanitarian system, protection risks, and conflict dynamics in South Sudan.

- Willingness and ability to travel to remote field locations.

Skills and knowledge:

- Strong skills in qualitative (drill down approach) and quantitative data analysis.

- Strong experience in questionnaire development, interview techniques and managing focus group discussions.

- Strong analytical skills and proficiency in both qualitative and quantitative research methods.

- Excellent communication and report-writing skills.

- Familiarity with the context and challenges of displaced populations and humanitarian response.

Language requirements:

- Written and spoken fluency in English

- Working knowledge of Arabic (Juba Arabic) is an added advantage

# 10. Technical supervision

The selected consultant will work under the supervision of the Chief of Party with the technical support of the MEAL Coordinator.

The Chief of Party in consultation with the MEAL Coordinator will lead the overall coordination and facilitation of the Final evaluation, including enumerator selection and hiring, providing lists of program sites and numbers of direct beneficiaries for all activities, sharing relevant program documents, advising about local protocols, making logistical arrangements, including accommodation and transportation for field data collection, connect the assessment team with the beneficiaries  and key informants, arrange meetings between the consulting team and beneficiaries, community members, authorities, and community leaders.

# 11. Location and support

The Final evaluation will be conducted in Upper Nile State (Malakal, Fashoda and Manyo Counties) and Abyei Administrative Area (Rumameer, Amenth-Aguok, Alal, Abyei Town Counties) as well as one additional location to be confirmed at a later stage. The consultant will be based partly in the field and partly remotely. DRC will provide logistical and administrative support, including access facilitation, introductions to stakeholders, and use of office space where available.

The Consultant will use their own computers and mobile telephones during the consultancy period. DRC will provide the mobile tablets/device to support the quantitative data collection

# 12. Travel

- DRC will facilitate only all in country travels to the fields related to this Final Evaluation including accommodation. However, the consultants shall provide for their own meals.

- Consultants contracted by DRC shall also be covered by their own travel insurance when travelling.

- DRC still has a responsibility and duty of care for the consultants, especially in contexts with a high Safety Level. The consultant is expected to follow and adhere to all governing Safety and Security procedures and rules.

# 13. Duty of Care

Duty of care is a Consultant firm’s responsibility. The consultant firm is liable for their own liability insurance for any damage or injury the consultant may inflict on any persons or objects during the performance of work.

# 14. Submission process

- Bids submission is strictly by email to the following dedicated, controlled, & secure email address: tender.ssd@drc.ngo

- Bids can be sent in multiple emails.

- No physical bids submission shall be accepted.

# 15. Evaluation of bids

- The RFP shall go under three stages of evaluation namely Administrative, Technical and Financial evaluation respectively.

- Only vendors that qualified at technical evaluation will be contacted for an interview with the panel to ensure their understanding of the consultancy services.