## BoQ
Proposed Bill of Quantity for Borehole drilling
The quantities stated against each item of the Bill of Quantities (BOQ) are the estimated quantities and are therefore provisional. The contractor shall be paid for actual quantities used.
S/N | Description | Unit | Qty | Unit price USD | Amount USD
1. Preliminary and general
1.1 | Mobilization of personnel, equipment and materials | lumpsum | 1
1.2 | Geo physical survey Perform VES ground water survey and determine most potential and appropriate location for high yield borehole. The survey must be conducted by an experienced Hydrogeologist consultant /expert. Including preparation and submission of hydrogeological report | lumpsum per BH | 4
Subtotal 1. Preliminary and general
2. Borehole construction
2.1 | Drilling to a maximal depth of 90m Note: depth depending on geo physical survey (most boreholes in the area are 40m deep and the water intake is above 20m depth) | m of drilling | 160
2.2 | Sampling and storage of drill cuttings at 2m intervals or as instructed by Engineer | lumpsum per BH | 4
2.3 | Supply and installation of UPVC casings (5"ND) 3M long x 170mm (5") external diameter with a minimum thickness of 3mm including end cap (average of 40m minus the length of the screen) | # pipes | 38
2.4 | Supply and installation of UPVC screens (5"ND ) 3M long x 170mm (5") external diameter with a minimum thickness of 3mm (average of 12m per BH) | # pipes | 16
2.5 | Supply and installation of gravel pack with uniform grading between 2.5 and 4.0 mm diameter from clean river gravel (5m3 per BH) | m3 | 20
2.6 | Well developed during a minimum of 6 hours until a stabilized satisfactory yield is reached and the turbidity is less than 5 NTU clear water according to technical specifications | hrs | 24
2.7 | Supply and installation of cement grouting of 1m diameter and 4m depth below the ground level, with all required activities, around the casing to act as sanitary seal (1m3 per BH) | m3 | 4
Subtotal 2. Borehole construction
3. Test pumping
3.1 | Perform a minimum of 6 hours constant rate test and recovery data are to be reported on standard borehole log. At least a yield of 5,000 ltrs/h is realized as per installation | lumpsum per BH | 4
Subtotal 3. Test pumping
4. Water quality analysis
4.1 | Water sampling, physical test, bacteriological and chemical test analysis, Original copies of results of the Water quality testing, showing date of sampling and date of analysis must be availed by contractor prior to payment for drilled borehole. The analysis to be checked against GOSS and WHO standards, and levels to be permissible before further construction. | lumpsum per BH | 4
4.2 | Clean and disinfect the borehole with chlorine solution of 50mg free clorine per liter with all required related activities. | lumpsum per BH | 4
Subtotal 4. Water quality analysis
5. Hand pump installation
5.1 | Supply and installation of pedestral, water tank, pump head assembly and cylinder | set | 4
5.2 | Supply and installation of India Mark II raiser pipes with sockets and connecting rodes (according to water level and pump test; average of 6 pipes) | set | 28
Subtotal 5. Hand pump installation
6. Head work
6.1 | Reinforced Concrete construction of apron (diameter 2m, raised 30cm to allow proper drainage) and installation of the hand pump pedestal & third plate, to cover the borehole. Construction of a drainage channel (6m long). Keep moist for at least 72 hours. | pc | 4
6.2 | Excavation and construction of soak away pit (2m deep) filled up with stones | pc | 4
6.3 | Cleaning the working site and removing all of the unnecessary items | sites | 4
6.4 | completion reports | sites | 4
Subtotal 6. Head work
TOTAL
Note: Grand total should include all costs associated with the drilling works including but not limited to company overhead, labor, materials, transport and 10% withholding tax on services. Contractors are advised to familiarize themselves with the site location in order that they may know the cost of transport.

## timeline
Proposed work plan for drilling of 4 boreholes in Bussere Payam
Starting date:
Date of completion:
Contract duration (calendar days):
S/N | Description of activity | Duration in weeks
|  | 2021-02-01 |  | 2021-03-01 |  |  |  |  | 2021-04-01
|  | CW 8 | CW 9 | CW 10 | CW 11 | CW 12 | CW 13 | CW 14 |  | CW 15 | CW 16 | CW 17 | CW 18
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## personnel
List of technical personnel
Name | Contact information | position in the company/ project | personnel details (Qualification and Experience)

## equipment
List of equipment
Note: all drilling equipment shall have the capacity to construct 178mm and 229 mm resp. 7" and 9" diameter lined boreholes including gravel packs to depths of up to 100m.
Equipment | Qty | Make, brand and age | Condition (new, good, poor) | Remarks (owned or to be hired)

## experience
Projects undertaken
S/n | Project name | Site | Type of work performed | Year of completion | Financial magnitute | Contactable persons that funded project (include email and phone contact)