## Giyada PS
BOQ For Upgrading borehole handpump, construction of hand washing facility and Water Collection Points and latrine manner maintenace work at Giyada primary School- Kator Town Block Council
S/n | Describtion | Unit | Qantity | Unit rate (USD) | Amount (USD)
1 | Site preparation, setting out , cleaning mobilization and demolization
1.01 | Pre- construction, survey, and cleaning of the top soil 20 cm depth | L-S | 1 | 0 | 0
| Sub-Total 1 |  |  |  | 0
2 | Earth works
2.01 | Excavate in ordinary soil for foundationf footings adv. Depth of 2.0m and pipelines at adv.depth of 0.5m. | Cu-m | 55 | 0 | 0
2.02 | Backfill and well compact with marrum around all foundations, footings, Handwashing facilities and drinking water points | Cu-m | 25 | 0 | 0
2.03 | Supply and level a coarse aggregate at the floor of the water tower with a thickness of 15 cm | Cu-m | 2.4 | 0 | 0
| Sub-Total 2 |  |  |  | 0
3 | Concrete, rebar and construction works
3.01 | Cast a concrete M15 for the footing base,Short column(40x40cm), beam(35X25), floor slab at (15cm thickness) for the water tower,Water Collection Point (WCP) and its floor (10cm thickness), Handwashing facilities and at the bottom of the chain link fence 40x30cm including all the formworks | Cu-m | 15 | 0 | 0
3.02 | Reinforced concrete for footing, short column and plateform of the WCP and Handwashing facilities in @ mixed ratio M20 filled in the form works and vibrated around rod reinforcement including all the formwork | Cu-m | 10 | 0 | 0
3.03 | Use a high tensile steel bars (12mm and 8mm) including cutting bending tying,hooking and fixing. 32No.Y12@15cm c'c for basement and cloumn reinforcement bar 8NoY12@13cm c'c per column | Kg | 110 | 0 | 0
3.04 | Install a set of dia. 18mm anchor bolts (4pcs) casted in concrete and a metal plate (35x35cm & 8mm thick) accurately in position for the steel tower columns complete with all its necessary accessories | set | 4 | 0 | 0
| Sub- Total 3 |  |  |  | 0
4 | Installation of the Metallic Structures and the Tank Segments
4.01 | Mounting,fabrication and Painting of Metal members for Water Tower. Refer and follow Teachnical Specification, Scope of work and approved work Drawings | L-S | 1 | 0 | 0
4.02 | Supply and place plastic water storage of 10,000 liters plastic water storage on the metal water Tower with inlet, outlet, washout and overflow acess in the tank will be designed in supervision of the site engineer | L-S | 1 | 0 | 0
4.03 | Fabricate and Install a metal ladder to the tank top as specs | L-S | 1 | 0 | 0
| Sub- Total 4 |  |  |  | 0
5 | Piping, Water distribution network, well cover, Valves and taps
5.01 | Supply and installation of (HDPE flexible) PE 100 pipe OD63 PN10 wall thickness 5.8mm as a riser from the pump to surface including all necessary fittings with consideration of turdity is less than 5 | M | 40 | 0 | 0
5.02 | Supply and installation of UPVC pipe (2.0)as a riser(column)from the ground surface to eleveted water Storage Tank including all necessary fittings for inlet and outlet such as water flow meter and well cover | M | 12 | 0 | 0
5.03 | Supply and installation of (HDPE flexible) PE 100 pipe OD63 PN10 wall thicks 3mm (1.0)as main distribution line with a value at the joint which leads to the three community water point and washout access and other neccessay requirements at an adverage depth of 50cm | M | 300 | 0 | 0
| Sub -Total 5 |  |  |  | 0
6 | Solar and water pump installation
6.01 | Dismentle the existing hand pump and assembly using ground fos submersible pump SQF 3A- 10 capacity well head protection, and pump controller cu- 200 in metallic box with padlock including all necessay requirements as such sensor for water control | pcs | 1 | 0 | 0
6.02 | Supply and install a solar panel of 335 watts welded on (40x40x2mm)angle bar on the top of the water tank and one independent security solar light 35 watts | pcs | 4 | 0 | 0
6.03 | Use elctical flate cable 4mm With Lightening arrester from the solar panels to the water pump with all necessay requirements | M | 50 | 0 | 0
| Sub-Total 6 |  |  |  | 0
7 | Fencing for the Water Tower and Water Collection Points
7.01 | Fabricate and paint and plotted in concrete an angle bar of (50x50x4mm) at the hieght of 2.0m@2c'c V- shape at the top and sheltered with chain link wire and an entry gate of 1.0m single shutter using Hollow section metal of 9No.40x40x4mm and considering barbed wire on top including all necessary requirements pad locks in and outside | M | 50 | 0 | 0
| Sub-Total 7 |  |  |  | 0
8 | Construction Hand washing facility with a shelter, Water Collection Plateform, Grease trape and Soakway pits
8.01 | Excavate in ordinary soil a strip foundation of Handwashing facility and ramp, WCPS, Soak way pit and a grease trap | Cu-m | 5 | 0 | 0
8.01 | Cast a concrete @ mixed ratio of M20 at handwashing facility, water collections ponits and grease trap | Cu-m | 4 | 0 | 0
8.02 | Construct 200mm brick wall for the excavated foundations, Walls, ramp, washing facilities and a sink at MHM room in well burnt clay bricks bedded and jointed 1:4 cement sand mortar | Sq. m | 37 | 0 | 0
8.03 | Cast 100mm reinforced concrete of M15 mix for top slab of hand washing facility,metalic angle bar for manhole, for grease trap the manhole is supported with an angle bar and WCP taps including formworks | Cu-m | 1.5 | 0 | 0
8.04 | 13mm thick cement sand (1:4) plaster interior wall handwashing facilities , Manholes, water plateform rendered in cement mortar | Sq. m | 20 | 0 | 0
8.05 | Tiling walls for hand washing facility, WCP floor and wall and MHM room upto window level, @cement sand 1:4 ratio where all edges are supported by tile trims. | Sq. m | 25 | 0 | 0
8.06 | Extending roof of the latrine with corrugated iron sheet G28 nailed at a metal of 30x30x1.2mm as purline and 40x40x2mm as rafter and 100x100x4mm as pole including fabrication,installation and painting | Sq. m | 21 | 0 | 0
8.07 | backfill the soakaways excavated pits with a suitable materials, place a pvc material and properly covered | no | 7 | 0 | 0
8.08 | provide a fence at the hand washing facilities ue 40x40x2mm hollow section metall at the spacing of 0.1c/c and a door on 2.0x 1.0 using with in and out locking system at the handwashing facilities | M | 21 | 0 | 0
| Sub Total 8 |  |  |  | 0
9 | Plumping works for Hand Washing Facility and four Water collection points
9.01 | Use UPVC pipe of 3/4'' connected to 8 taps on GI Pipe for handwashing facilities and 4 taps with each WCP and Handwashing facility 1 control flage valve for with GI pipe fabricated metal of on the wall, waste water is directed to soak away pit via grease trap | No | 4 | 0 | 0
| Sub Total 9 |  |  |  | 0
10 | Manner Maintance Work at the 3 latrine blocks
10.01 | Supply and installing of metal doors including fabrication and painting; in square (20X20) and rectangular hollow section metal with proper in and out locking system including big size 2 padlocks | No | 7 | 0 | 0
10.02 | Re-Cast plain 100mm concrete for the on corrider, Ramp at both entry | Cu-m | 2 | 0 | 0
10.03 | Re-Desigining foot resting, drop hole and floor per standard and rendering smooth cement mortar with red oxide on concrete floor (Smoothing). | Sq. m | 63 | 0 | 0
10.04 | Fabricate, paint and install hollow section metal of 30x30x1.2 mm at the spacing of 100m c/c above the curtain wall as showing in the drawing | M | 27 | 0 | 0
10.05 | Repair the broken doors of the existing latrine blocks | No | 2 | 0 | 0
10.07 | Rought cast plastering for the exterior wall of all the three latrine blocks | Sq. m | 121.2 | 0 | 0
10.08 | Extend the existing roof of latrine to the curtain wall using hard timber of 2x4 rafter and 2x3 purline nailed at metalic wall plate | Sq. m | 39 | 0 | 0
10.09 | Re- Painting and Fixing cracks Prepare surface smooth with white cement , apply primer coats and three coats of plastic emulsion paint to exterior and interior walls. | Sq. m | 121.2 | 0 | 0
| Sub Total 10 |  |  |  | 0
Grand Total |  |  |  |  | 0
Important Note
1 | Rehabilitation of 3 block of latrine at School for Kindergade, Girls, and Boys
2 | Solarising 1 well at the center of the school with water Tower and extends the water pipeline to the each of the schools and community taps
3 | Construction of 4 Water Collection Points each with well fence and has its grease trap and soakaways
4 | Construction of Hand washing facility at 3 schools with its grease trap and hand washing facility

## St. Kizito PS
BOQ For Upgrading borehole handpump, construction of hand washing facility and Water Collection Points withdrainage system and1 block of latrine manner maintenace work at St. Kizito PHCC- Munuki Town Block Council
S/n | Describtion | Unit | Qantity | Unit rate (USD) | Amount (USD)
1 | Site preparation, setting out , cleaning mobilization and demolization
1.01 | Pre- construction, survey, and cleaning of the top soil 20cm depth | L-S | 1 | 0 | 0
| Sub-Total 1 |  |  |  | 0
2 | Earth works
2.01 | Excavate in ordinary soil for foundation footings adv. Depth of 2.0m and pipelines at adv.depth of 0.5m. | Cu-m | 40 | 0 | 0
2.02 | Backfill and well compact with marrum around all foundations, footings, Handwashing facilities and drinking water points | Cu-m | 18 | 0 | 0
2.03 | Supply and level a coarse aggregate at the floor of the water tower with a thickness of 15 cm | Cu-m | 2.4 | 0 | 0
| Sub-Total 2 |  |  |  | 0
3 | Concrete, rebar and construction works
3.01 | Cast a concrete M15 for the footing base,Short column(40x40cm), beam(35X25), floor slab at (15cm thickness) for the water tower,Water Collection Point (WCP) and its floor (10cm thickness), Handwashing facilities and at the bottom of the chain link fence 40x30cm including all the formworks | Cu-m | 5.5 | 0 | 0
3.02 | Reinforced concrete for footing, short column and plateform of the WCP and Handwashing facilities in @ mixed ratio M20 filled in the form works and vibrated around rod reinforcement including all the formwork | Cu-m | 7.1 | 0 | 0
3.03 | Use a high tensile steel bars (12mm and 8mm) including cutting bending tying,hooking and fixing. 32No.Y12@15cm c'c for basement and cloumn reinforcement bar 8NoY12@13cm c'c per column | Kg | 110 | 0 | 0
3.04 | Install a set of dia. 18mm anchor bolts (4pcs) and a metal plate (35x35cm & 8 mm thick) accurately in position for the steel tower columns complete with all its necessary accessories | pcs | 4 | 0 | 0
| Sub- Total 3 |  |  |  | 0
4 | Installation of the Metallic Structures and the Tank Segments
4.01 | Mounting,fabrication and Painting of Metal members for Water Tower. Refer and follow Teachnical Specification, Scope of work and approved work Drawings | L-S | 1 | 0 | 0
4.02 | Supply and place plastic water storage of 10,000 liters plastic water storage on the metal water Tower with inlet, outlet, washout and overflow acess in the tank will be designed in supervision of the site engineer | L-S | 1 | 0 | 0
4.03 | Fabricate and Install a metal ladder to the tank top as specs | L-S | 1 | 0 | 0
| Sub- Total 4 |  |  |  | 0
5 | Piping, Water distribution network, well cover, Valves and taps
5.01 | Supply and installation of (HDPE flexible) PE 100 pipe OD63 PN10 wall thickness 5.8mm as a riser from the pump to surface including all necessary fittings with consideration of turdity is less than 5 | M | 40 | 0 | 0
5.02 | Supply and installation of UPVC pipe (2.0)as a riser(column)from the ground surface to eleveted water Storage Tank including all necessary fittings for inlet and outlet such as water flow meter, and well cover | M | 12 | 0 | 0
5.03 | Supply and installation of (HDPE flexible) PE 100 pipe OD63 PN10 wall thicks 3mm (1.0)as main distribution line with a value at the joint which leads to the three community water point and washout access and other neccessay requirements at an adverage depth of 50cm | M | 150 | 0 | 0
| Sub -Total 5 |  |  |  | 0
6 | Solar and water pump installation
6.01 | Dismentle the existing hand pump and assembly using ground fos submersible pump SQF 3A- 10 capacity well head protection, and pump controller cu- 200 in metallic box with padlock including all necessay requirements as such sensor for water control | pcs | 1 | 0 | 0
6.02 | Supply and install a solar panel of 335 watts welded on (40x40x2mm)angle bar on the top of the water tank and one independent security solar light 35 watts | pcs | 4 | 0 | 0
6.03 | Use elctical flate cable 4mm With Lightening arrester from the solar panels to the water pump with all necessay requirements | M | 50 | 0 | 0
| Sub-Total 6 |  |  |  | 0
7 | Fencing for the Water Tower and Water Collection Points
7.01 | Fabricate and paint and plotted in concrete an angle bar of (50x50x4mm) at the hieght of 2.0m@2c'c V- shape at the top and sheltered with chain link wire and an entry gate of 1.0m single shutter using Hollow section metal of 9No.40x40x4mm and considering barbed wire on top including all necessary requirements pad locks in and outside | M | 34 | 0 | 0
| Sub-Total 7 |  |  |  | 0
8 | Construction Hand washing facility with at shelter, Water Collection Plateform, Grease trape and 2 two Soakway pits
8.01 | Excavate in ordinary soil for a strip foundation of Handwashing facility and ramp, WCPs, Soak way pit and a grease trap | Cu-m | 5 | 0 | 0
8.01 | Cast a concrete @ mixed ratio of M20 at handwashing facility, water collections ponits and grease trap | Cu-m | 4 | 0 | 0
8.02 | Construct 200mm brick wall for the excavated foundations, Walls, ramp, washing facilities and a sink at MHM room in well burnt clay bricks bedded and jointed 1:4 cement sand mortar | Sq. m | 30 | 0 | 0
8.03 | Cast 100mm reinforced concrete of M15 mix for top slab of hand washing facility,metalic angle bar for manhole, for grease trap the manhole is supported with an angle bar and WCP taps including formworks | Cu-m | 1.5 | 0 | 0
8.04 | 13mm thick cement sand (1:4) plaster interior wall handwashing facilities , Manholes, water plateform rendered in cement mortar | Sq. m | 15 | 0 | 0
8.05 | Tiling walls for hand washing facility, WCP floor and wall and MHM room upto window level, @cement sand 1:4 ratio where all edges are supported by tile trims. | Sq. m | 20 | 0 | 0
8.06 | Extending roof of the latrine with corrugated iron sheet G28 nailed at a metal of 30x30x1.2mm as purline and 40x40x2mm as rafter and 100x100x4mm as pole including fabrication,installation and painting | Sq. m | 15 | 0 | 0
8.07 | Backfill the soakaways excavated pits with a suitable materials, place a pvc material and properly covered | no | 4 | 0 | 0
| Sub Total 8 |  |  |  | 0
9 | Plumping works for 2 Hand Washing Facility and 2 Water Collection point
9.01 | Use UPVC pipe of 3/4'' connected to 8 taps on GI Pipe for handwashing facilities and 4 taps with each WCP and Handwashing facility 1 control flage valve for with GI pipe fabricated metal of on the wall, waste water is directed to soak away pit via grease trap | no | 2 | 0 | 0
| Sub Total 9 |  |  |  | 0
10 | Manner Maintance Work for 1 block latrine at the School
10.01 | Supply and installing of metal doors including fabrication and painting; in square (20X20) and rectangular hollow section metal with proper in and out locking system including big size 2 padlocks | No | 6 | 0 | 0
10.02 | Re-Cast plain 100mm concrete for the on corrider, Ramp at both entry | Cu-m | 1.5 | 0 | 0
10.03 | Re-Desigining foot resting, drop hole and floor per standard and rendering smooth cement mortar with red oxide on concrete floor (Smoothing). | Sq. m | 14.2 | 0 | 0
10.04 | Fabricate, paint and install hollow section metal of 30x30x1.2 mm at the spacing of 100m c/c above the curtain wall as showing in the drawing | M | 10 | 0 | 0
10.05 | Repair the existing doors of the latrine block | No | 4 | 0 | 0
10.06 | Extend the existing roof of latrine to the curtain wall using hard timber of 2x4 rafter and 2x3 purline nailed at metalic wall plate | Sq. m | 39 | 0 | 0
10.07 | Re- Painting and Fixing cracks Prepare surface smooth with white cement , apply primer coats and three coats of plastic emulsion paint to exterior and interior walls. | Sq. m | 76.2 | 0 | 0
| Sub Total 10 |  |  |  | 0
| Grand Total |  |  |  | 0
Important Note
1 | Rehabilitation of 1 block of latrine at School
2 | Solarising 1 well at the PHCC with water Tower and extends the water pipeline to the school
3 | Construction of 2 Water Collection Points for PHCC and near by (St. Kizito School) each with its grease trap and soakaways
4 | Construction of Hand washing facility at school with its grease trap and hand washing facility