Terms of Reference for MID-TERM EVALUATION

Reducing hunger and malnutrition and promoting resilient food production in Cueibet County / Gok State, South Sudan

(PROMISE)

Project location: Cuibet County

Gok State

South Sudan

Project Contract Period:  1st September 2016 – 31st August 2023

Funded by: BMZ through Development Diakonie Katastrophenhilfe

Implemented by: Vétérinaires sans Frontières - Germany (VSF-G)

0ctober 2019

Glossary

CAD              	County Agriculture Department

CAHW            	Community Animal Health Worker

CLD               	County Livestock Department

FGD                	Focus Group Discussion

FS                    	Food Security

GOSS             	Government of the Republic of South Sudan

HH                  	Household

IDP                 	Internally Displaced Person

INGO              	International Non-Governmental Organization

KII            	Key Informant Interview

LRRD              	Linking Relief, Rehabilitation and Development

NFI                  	Non Food Item

QA                	Quality Assurance

ROSS              	Republic of South Sudan

RRC               	Relief and Rehabilitation Commission

SMAF             	State Ministry of Agriculture and Forestry

SMARF           	State Ministry of Animal Resources and Fisheries

TOR              	Terms of Reference

VSF        	Veterinaries San Frontiers – South Sudan

Table of Contents

1.	Project Summary	6

2.	Background and context	7

2.1.	Overall description	7

2.2.	Project objectives and results	8

3.	Evaluation purpose and target audience	9

4.	Evaluation objectives and scope	10

5.	Evaluation tasks and questions	11

6.	Approach and methodology	12

7.	Timing and deliverables	13

7.1.	Inception report	13

7.2.	Draft mid-term evaluation report	13

7.3.	Final mid-term evaluation report	13

7.4.	Roles and responsibilities	14

7.5.	Tentative itinerary	15

8.	Evaluation team composition and required competencies	16

9.	Management arrangements	16

10.	Budget and payment	17

11.	Proposal submission	18

- Project Summary

| Contract Beneficiary | Vétérinaires Sans Frontieres Germany |
| --- | --- |
| Project Title | Reducing hunger and malnutrition and promoting resilient food production in Cueibet County / Gok State, South Sudan (PROMISE) |
| Location | Cuibet County, Gok State, South Sudan |
| Project Duration | 1 September 2016 to 31st August 2023 |
| Project Phase | Second Phase |
| Assessment Type | Mid Term Evaluation |
| Evaluation Purpose | To document and inform the stakeholders (donors, partners and beneficiaries) on the program’s achievements so far against set objectives and targets with due reference to relevance, effectiveness, and sustainability; the potential impact in relation to relevant VSF Germany policies and BMZ standards, the challenges and the lessons learned for project improvement in the next period. |
| Evaluation Objectives | To assess the overall performance of the project against the baseline data established at the start of the project. |
|  | To assess progress in the achievements of outcomes, outputs and activities |
|  | To assess the scope, quality and relevance of the project outputs produced so far in relation to the project theory and design |
|  | To provide actionable, context appropriate and innovative recommendations for project improvement in the next implementation period |
| Methodology | Programme mid-phase evaluation using OECD-DAC principles |
|  | Focus Group Discussion and key informant interviews Review of available secondary data |
|  | Household survey |
|  | Observation Qualitative and quantitative Anthropometry, Household Economy Analysis GPS mapping Case/tracer studies/Most significant change stories |
| Evaluation Start and End dates | 1st to 14th March 2020 |
| Anticipated Evaluation report release dates | 30th April 2020 |

- Background and context

  - Overall description

- Background

Vétérinaires Sans Frontières (VSF) is an international Non-Governmental Organization, providing humanitarian aid and development assistance to pastoralists and vulnerable communities in areas where livestock is of importance. VSF support is in animal health; livestock related agriculture, marketing, food safety, drought responses and mitigation, capacity development of communities and governmental institutions, peace and conflict resolution with the ultimate aim of food security and strengthened livelihoods of pastoralist communities.

In South Sudan VSF has been implementing a BMZ funded project - Reducing hunger and malnutrition and promoting resilient    food production in Cueibet County / Gok State, (PROMISE). Implementation of the 89month project started in September 2016 and is scheduled to end in August 2023. The project is being implemented in Cueibet County, Gok (Lakes) state of the Republic of South Sudan in a predominantly agro-pastoral community.

PROMISE supports activities aimed at improving food security and reducing malnutrition within vulnerable populations. It addresses structural issues leading to hunger and malnutrition in a bid to resolve these in the medium or long term, with an emphasis on developing sustainable solutions. PROMISE aims to contribute to this global objective by building capacities of target households in innovative and sustainable agricultural practices as well as strengthened resilience against conflict and climatic risks.

- The 3 key result areas of the Project are:

Result 1: Contribution from 47schools to intermediate and long-term nutritional security and resilient livelihoods of the population realized.

Result 2:  Innovative, adaptable and sustainable agricultural and or livestock production practices are adopted to reduce the annual food gap.

Result 3:  Contribution from socio-ecologically resilient productive natural resources management realised for improved livelihoods and decreased conflicts.

A baseline (formative) evaluation was carried out and completed in December 2016 and project monitoring missions carried out in July 2017 and November 2017. Six semi-annual reports covering the period 1 September 2016 to 30 June 2019 have been submitted to the Diakonie.

The end of first phase of PROMISE was in June 2019, for which matter VSF is seeking to conduct a mid-term evaluation that is “resilience” and “outcome & impact” oriented, participatory, and builds on action research with a focus on innovation and learning.  It will be based on a participatory mix of methods including internal & external assessments, looking into the future as much as into the past, involving community members and “beneficiaries” not only into data collection but also into a feedback loop of data analysis and reflection on the way forward as much as possible. The evaluation will include summative elements (with regards to Phase I) as well as formative elements (informing implementation of Phase II).

The review will be participatory with valid inputs from all the relevant stakeholders such as beneficiaries, local and state agriculture and livestock officials, VSF Staff, DKH and other community stakeholders.

  - Project objectives and results

Overall Objective: To contribute to increased food security, reduced malnutrition and resilient livelihoods for vulnerable households in Lakes/Gok State, South Sudan

Specific Objective1: Acute malnutrition in Cueibet is reduced. Specific Objective 2: Households have adopted innovative, adaptable and sustainable agricultural and/or livestock production practices which allow them to significantly reduce their average food gap per year. Specific Objective 3: The livelihoods of the target group are strengthened and more resilient against conflict and climate risks.

Results 1: Contribution from 47schools to intermediate and long-term nutritional security and resilient livelihoods of the population realised.

Outcome - 15,000 school children in 47 schools receive 1 meal daily during periods of acute food deficits - SAM and GAM levels amongst 15,000 school-going children in 47 schools are reduced by at least 1% for SAM and 5 % for GAM for both girls and boys alike - Model-gardens will be able to contribute to at least 15% to the diet of school children Indicators - # of School children receiving one meal every day during periods of acute food deficiency - % increase in school enrollment and retention throughout the period of school feeding - % increase in incomes from agro-pastoral production and NRM. - # of Functional kitchen- and model-gardens that supplement the diet of school children even after the school feeding has come to an end

Result 2. : Innovative, adaptable and sustainable agricultural and or livestock production practices are adopted to reduce the annual food gap

Indicators - % decrease in food gap by the end of the project - Food intake diversified - # of Innovative and climate adapted agro-pastoralist production methods practiced

Result 3. Contribution from socio-ecologically resilient productive natural resources management realized for improved livelihoods and decreased conflicts

Outcome - Contribution from socio-ecologically resilient, productive natural resources management realized for improved livelihoods and decreased conflicts Indicators - % of Households engaged in productive natural resources management and generating additional income and practicing diversified production and income earning strategies - # of Project based conflict resolution mechanisms established and functional - # of Recommended natural resource management techniques introduced and adopted

- Evaluation purpose and target audience

  - Evaluation type

This is a mid-interim evaluation to assess the progress made by the project towards achieving planned activities and results as set out in the project design. It aims at capturing the progress attained towards addressing the project objectives.

  - Purpose

The purpose of the mid-term evaluation is to carry out an overall appraisal of the efficiency, relevance and sustainable progress of project towards meeting its objective so as to provide decision-making information for use to improve the quality and relevance of the project and its implementation; and to identify necessary reorientations and follow-up actions in the remaining period to ensure the achievement of the original objectives.

  - Target audience

- BMZ, Bread for the World, and Development Diakonie Katastrophenhilfe

The mid-term evaluation shall provide the donor BMZ and Diakonie with information on how the project is performing towards finally contributing to the final objectives of the program and what follow-up actions may be necessary to ensure the desired outcomes and project re-designing to suite the context dynamics.

- VSF Germany and partners

The mid-term evaluation shall provide VSF and its partner’s opportunity to critically assess technical arising issues and mechanisms and meticulously focus on the recommendations to improve the pathways and potential of PROMISE to achieve expected outcomes and objectives within the project timeframe.

- Beneficiaries and stakeholders

The mid-term evaluation process will accord beneficiaries and stakeholders opportunity to participate in the review process, build the capacity for effective participation in reviews, and enhance ownership and accountability of the implementing partners. The exercise will enable improvement of the relevance of the project to the needs of the beneficiary and priorities of the stakeholders.

- Evaluation objectives and scope

The overall purpose of the evaluation is to assess the progress made towards achieving expected outputs and outcomes and identify and document lessons-learned and to make recommendations to improve the project. The evaluation shall further coagulate the arising issues in to actionable element aimed at improving the current project status.

  - Evaluation objectives

- To appraise and establish the relevance of the project

The evaluation will appraise the appropriateness of project objectives to the problems that it was supposed to address, and to the physical and policy environment within which it operates. This will include an assessment of the quality of project preparation and design – i.e. the logic and completeness of the project planning process, the internal logic and coherence of the project design.

- To determine the level of efficiency of the project implementation

Project efficiency will be evaluated by gauging whether the progress made towards achieving the expected results is happening at a reasonable cost – how efficiently Means and Activities are being converted into Outputs.

- To determine the effectiveness of the project implementation

The mid-term evaluation will determine the contribution made by project Outputs towards achieving the Project Objectives, and how Assumptions have affected project achievements.

The evaluation shall also determine the effectiveness of the employed approaches in addressing the primary challenges affecting the community. The linkage and resultant synergy between these respective components shall be appraised.

- To determine the project quality

The evaluation shall appraise PROMISE against desirable project quality factors that include: Participation and ownership by beneficiaries; Policy conformity; Appropriate technology; Socio-cultural implications; Gender equality; Environmental protection; Local institutional development; and Management capacities; and Financial and economic viability. Any deviation from initial plans shall be evaluated and accounted for. Achievements made in respect of the exit strategy will be gauged.

- To provide actionable, context appropriate and innovative recommendations for project improvement and future programming.

- Accountability for continuous learning and improvement (Core Humanitarian Standard (CHS) #7).

- Utilize CHS (incl. OECD-DAC) as a basis for ex-post summative evaluation and accountability.

- Engage in more explorative study to identify overall outcomes and impact against the backdrop of a “Resilience Framework “(from the perspectives of capacities of communities) and to identify potential shortcomings in this respect as a crucial basis to improve approaches in the second phase.

- Engage communities (focus on school feeding committees and other groups established), in action-research and a visioning exercise that borrows from PVCA (Participatory Vulnerability and Capacity Assessment), SCLR (Supporting Community-Led Response) to reflect on assessment results and to identify potential to enhance resilience of communities to maintain educational outcomes and food security with “own means“ WITH the support and facilitation of the project for the next 5 years and WITHOUT upon exit (based on a “Resilience “/LRRD framework).

- Identify Gender impact and unutilized potentials

  - Scope of the evaluation

The mid-term review period will focus on the past 34months of project implementation from September 2016 to June 2019 in the targeted project areas in Cueibet County. The evaluation will cover in detail programming quality as well as protection and equality topics.

- Evaluation tasks and questions

- The evaluation tasks relate directly to the evaluation objectives and should be comprehensively addressed with reference to one another.

  - Determine the relevance of the project

- What is the prevailing project context and its significance to project implementation?

- Who are the key actors (stakeholders) in the project, what are their roles and responsibilities and how have they influenced project implementation?

- What is the relevance of the project objectives to the beneficiary, community, governance and policy priorities at project and how has this changed during the life span of the project?

- What are the strengths and weaknesses in project design and how have these impacted on project implementation and monitoring?

  - Determine the efficiency of the project

- What is the level of cost-effectiveness in the accomplishment of the outputs completed so far or in the process of completion?

- What is the quality of the outputs?

- What are the strengths and successes in project implementation (management, staff, coordination and reporting)?

- What are the weakness and challenges in project implementation (management, staff capacity, coordination and reporting)?

  - Determine the effectiveness of the project

- To what extent is the project meeting its objectives?

- To what extent has each of the approaches employed by the project contributed towards achievement of project objectives?

- What are the identified and potential barriers to successful delivery of the project?

- How have the assumptions made at project design evolved and how have they impacted on the project implementation and progress towards achievement of the objectives?

- What is the degree of project quality with reference to the evaluation’s desired project quality factors?

  - Determine progress towards impact and sustainability of results

- What is the degree of soundness and feasibility of the projects exit strategy and to what extent has it been implemented?

- What is the level of overall viability of the expected outcomes and signs of sustainability of the same?

- Approach and methodology

The assessment methodology proposed by the consultant(s) should include a mix of quantitative and qualitative data collection methods. The desired methodology is participatory and all the key stakeholders in the program including target beneficiaries, County Agriculture and County Livestock Department staff, will be considered to be part of the mid-term evaluation process. The evaluation will be based on the findings and factual statements identified from review of relevant documents including the project document, Annual Project Reports (APR), Project Implementation Reports (PIR), in addition to the technical reports produced by the project.

The anticipated benefit of a Participatory and stakeholder-centred approach is the empowering that the process will impart to those service providers and the beneficiaries/ stakeholders who will participate in the exercise. Focus group discussions, key informant interviews, site visits etc are proposed amongst the methods to be used for the review. The consultant will provide leadership and bear responsibility for the process, the findings, the comments and the content of the final document. VSF will be responsible for organizing the locations for conducting the Key Informant interviews, household questionnaire and Focus Group discussions in the respective payams of operation whilst the consultant will review and finalize the tools in conjunction with VSF Programming team. Participation of stakeholders in the evaluation should be maintained at all the times, reflecting opinions, expectations and vision about the contribution of the project towards the achievement of its objectives.

The general rule related to acceptable margins of error (5%) in social research will apply to the study. Sampling criteria should be agreed upon with VSF Country office, a 30 x 30 cluster sampling is recommended, however, the Consultant may have the discretion to employ any other sampling methodology upon giving appropriate justification which will then be reviewed by VSF and DKH program team before being adopted.

- Timing and deliverables

  - Inception report

- The inception report shall provide a detailed description of the methodology to answer the evaluation questions as well as the proposed source of information and data collection procedure. The inception report shall outline the contents of all the deliverables.

  - Draft mid-term evaluation report

- The consultancy team will develop draft evaluation report for review by the PROMISE program personnel and partners. The report shall be validated by stakeholders in a workshop setting and feedback incorporated into the report. The draft report will adopt the format of the final report as presented below under the final report. Generally, report will include the Executive summary, Intervention description, Evaluation purpose, Evaluation methodology, Findings, Conclusions (answers to the Evaluation Questions), Recommendations and Annexes (list of people interviewed, key documents consulted, data collection instruments, summary of the TOR). Further details will be found in the annexes.

  - Final mid-term evaluation report

- The consultancy team shall endeavor to develop the final report and present the output in an electronic format to VSF for final approval and adoption. The final report (Word, Excel files to be put in PDF as well) will be submitted according to the evaluation timeline. The report will have the following structure:

- Cover page (1 page)

- Table of Contents (1 page)

- Acknowledgements (1 page)

- Glossary (1 page)

- Introduction (1 page)

- Project being evaluated (1 page)

- Executive summary (2 Pages)

- Evaluation introduction/Background (max 2 pages)

- Methodology (max 2 pages)

- Findings (max 10 pages)

- Conclusion and recommendations (max 2 pages)

- Lessons learnt from the evaluation process (max 1 pages)

- Appendices (to include copies of all tools, list of enumerators, survey timeline including all KII and FGD participants and discussion transcripts, (as many pages as necessary- please reference the annexes in the report, but include them in a zip file as separate documents.

- The final report will be accompanied by the following deliverables:

- A 2-page evaluation fact sheet and soft copy of dataset. This is to include relevant findings from the evaluation, key points and recommendations.

- An Indicator Summary Sheet, giving status of all indicators measured in the HH questionnaire compared against baseline values

- Learning dossier - Lessons learnt by the entire evaluation team shall be documented and shared with the project team and Programs Office Juba so that they may be taken into consideration for future studies. The documentation of these lessons will be vital for reflection, growth and continued improvement. The lessons will be drawn from the process and the actual house hold surveys, key informant interviews, focus group discussions, study observations and secondary data reviews.

  - Roles and responsibilities

Each member of the evaluation team shall have designated roles and responsibilities for the delivery of the evaluation.

Scope of Work and responsible parties

- Evaluation tools are properly developed and in line with VSF G and BMZ evaluation standards - Review of the available relevant project documents i.e. project proposal, log frames. - Coordinate HH Interviews for selected respondents during the evaluation study. - Training of enumerators. - Conduct interviews with selected partners, staff and other - Visit selected project sites. Responsible: Consultant, Program Manager

- Coordination of the household interviews and well us providing guidance to the focus groups discussions - Household interview and FGD participants are properly selected - Guide the FGD and interviewers on proper data entry and documentation/filing - Prepare the summary reports of each FGD as per agreed upon format. - Ensure completeness of the survey instruments questionnaires Responsible: Consultant, Project Manager

- Apply effectively the quantitative and qualitative tools - Obtain consent from the household or FGD members to conduct the evaluation. - Record household data on questionnaire as per training instructions. - Record all key notes related to issues arising while interviewing. - Review and submit the survey data to survey team leader in accordance with the schedule Responsible: Consultant

- Provide overall coordination, logistics, and technical oversight in the Evaluation process. - Brief stakeholders about the purpose of the evaluation. - Brief stakeholders about the purpose of the evaluation. - Provide technical oversight and monitoring of the Survey and ensure timely completion and compliance with international evaluation standards. - Avail all project related secondary data. - Avail all the required logistics including vehicles for the Evaluation. - Assist in organizing meetings with stakeholders. - Avail all the required logistics including vehicles for the Evaluation. - Recruit and pay the evaluation enumerators. - Supervise adequate utilization of the resources allocated for the study. - Budget preparation and management during the evaluation period/ensuring that all expenses are properly documented. - Budget preparation and management during the evaluation period/ensuring that all expenses are properly documented. - Oversee accommodation and meals for data collection teams. Responsible: Project Manager and Consultant

  - Tentative itinerary

| Event | Responsible Persons | Timelines |
| --- | --- | --- |
| Preparation phase |  |  |
| Desk phase – secondary data review, tools development |  |  |
| Review – secondary data, information | Consultant | 1 |
| Data Collection Tools Development Share Data Collection tools with VSF Germany programs | Consultant Consultant | 2 |
| Field phase – data collection |  |  |
| Enumerators selection and Training | Consultant | 2 |
| Pretesting, refining and printing of evaluation tools | Consultant & project staff | 1 |
| Data collection and interviews | Consultant and Evaluation team | 6 |
| Synthesis phase |  |  |
| Data Analysis and validation | Consultant | 2 |
| Draft Report of Evaluation | Consultant | 1 |
| Final Report with Feed back | Consultant | 1 |
| Total Number of days excluding preparation and planning days |  | 16 Days |

- Evaluation team composition and required competencies

- The evaluation team shall compose of members with a comprehensive mix of competencies in agro-pastoral production and market systems and social research methodologies. These will be complemented with at least five years’ experience in related programming and program research. Extensive experience in the specific fields in the horn of Africa and South Sudan in particular will be required. Excellent communication skills and well as demonstrated writing and presentation skills are requisite.

- Management arrangements

The consultant should be informed of some issues, situation and conditions as they are or may arise during the exercise.

- Travel: All international flights land in Juba, it is not possible to fly to Rumbek and onwards to Cueibet on the same day. Rumbek flights are only during week days. The consultant should take in to consideration this challenge that should not lead to cancellation of the exercise. VSF will cover the cost of all internal flights and transport.

- Accommodation: Consultants will be housed in hotels in Juba and Rumbek whilst in Cueibet they will be housed at the organizations compound lodgings. However, electricity for powering laptops is not guaranteed at all times. Internet access will be available at VSF offices, but may not be available in the hotels.

- Data entry may not be possible in the field. VSF will not supply data entry clerks or equipment for data entry. Consultants are responsible for all data entry and management. All hard copies of tools will need to be transported by consultants to the place where data entry will be done. All data sets must be provided to VSF in soft copy at the time of submission. They are the property of VSF and the communities from which the data will be collected and may be used for future analysis.

Data will in most instances be collected from non-English speakers. However, tools will not be translated into the local language. A way around this matter will be developed in discussion with VSF program staff and the consultant.

- Operation arrangement

- Accommodation and transport will be provided by VSF;

- Translators, drivers, facilitators, office space, printing of questionnaires etc will be provided by VSF;

- The contact person in South Sudan will be the VSF Country Programs Manager;

- The focal person in the field will be the Project Manager;

- Security advisory issues will be provided by VSF;

- VSF will take care of internal travels but in case of international flights, the consultant will organize and DKH will pay reasonable prices incurred only.

- Reference materials

Relevant documents will be availed for the consultant to support during the secondary information desk reviews. The consultant will be encouraged to identify any other sources for appropriate additional information that may be required to supplement what is provided by the project.

The Project Team will share the following documents with the Consultants for reference.

    - Full project proposal

    - Project agreement contract

    - Baseline report

    - Project log frame

    - Project activity reports

    - Project first year report

    - Sudan Population and Housing Census report 2008

    - National Baseline Household Survey 2009

    - FAO/WFP food security assessment/survey reports

    - South Sudan Development Plan 2011-17

    - Humanitarian Response Plan 2016, 2017, 2018,

    - South Sudan Infrastructure Action Plan, Chapter 6

    - Investing in Agriculture for Food Security & Economic Transformation – UNDP

- Budget and payment

The evaluation budget will take care of the expenses such as the consultant’s charges, international travel, in country travel, accommodation full board, and fuel for vehicles to be used during the survey period, enumerators’ fees and lunches, stationery and communication costs. VSF will take care of the following

- Flights (internal for the consultant)

- Accommodation in South Sudan

- Field transport (fuel and car rentals)

- Enumerators fees

- Stationeries

The following costs will not be covered by the organization and should be factored into the consultancy and related fee which the consultant will submit with the application.

- Costs for data handling, entry and processing

- Communication cost.

- Report writing and printing.

- Any medical expenses by the consultant during the assignment

- Proposal submission

The proposals will be evaluated according to the following criteria;

- Technical and financial proposal

- Proposed personnel for the assignment

- Profile of the applicant - corporate or individual