## Sheet1
REINFORCED SECURITY wall pibor field office
PLAN INTERNATIONAL, JUBA, SOUTH SUDAN
Construction of RCC Security Wall for Plan Field Office in Pibor Republic of South Sudan
Quantities shown in the BOQ are purely indicative. The actual quantities will be estimated based on the execution by Contractor and the actual work performed on site. The amount of money to be paid for each item will be calculated based on the Unit Price mentioned in the Contract. The Contractor shall be responsible for providing all necessary personnel, supervision, tools, plants and equipment, materials, consumables, supplies, facilities including working and living accommodations, transportation, administration, insurance and all other costs required to fulfil all its contractural obligations.
| S/NO. | DESCRIPTION | UNIT | FINAL QTY | UNIT COST | FINAL TOTAL
A |  | To carry out survey and site visit to of the site (incluiding and not limited to material sourcing from Juba eg sand and aggregate) NOTE: Pibor sand is full of silt and do not meet the specifications from government laboratoriy tests. (refer instructions documents)
| A.1 | To carry out Survey | VS | 1
| A.2 | Preðare (Foundation with reinforment details, Wall Footings with reinforcement details, RCC Wall with reinforcement details, etc. for construction of RCC walls as per PLAN provided layout plan. Chief Engineer for approval prior to construction, (refer drawings) | WS | 1
Sub-Total
B |  | Excavation and Earthwork
| B.1 | Demolish existing Berm Wall and remove debris to an approved location in the compound, compact, ram well..clear site or debris, bushes and shrubs, remove debris and cart away to a suitable site and prepare the site for excavation | sqm | 1650
| B.2 | Excavation foundation trenches, width 1.8 m, Depth as per the instructions of the Supervising Engineer but not greater than 1.5 m, including dressing, ramming, and disposal o surplus soil within 50m lead | cum | 335
| B.3 | Excavation in foundation trenches in rocky soil, width 1.8 m, Depth as per the instructions of the Site Engineer including dressinB ramming, and leveling | cum | 91.67
| B.4 | Providing 100 mm thick well compacted execavated Marrum layer below the 50 mm thick Lean concrete base slab | cum | 165.65
| B.5 | Backfill selected excavated material around foundations as per the instructions of the Supervising Engineer | cum | 165.65
| B.6 | Lean PCC (M 15) for leveling foundations on rock areas and Embedding | cum | 27
Sub-Total
C
| C.1 | Provisional gates (6000x2400)mm and small gates(1200x2000) ref drawings (gate column 300x300mm concrete mix 1:2:4) refer drawings | no. | 2
| C.2 | Ramps, well done at the gates, allowing vehicle n pedestrian as per PLAN engineer instructions | no. | 1
| C.3 | Provision and installation ofLean PCC (M 1 5) under base slabs, 50 mm thick in, Cement, Sand and 20 mm aggregates, including loading, transportation, formworks and all the activities, materials, equipment and manpower necessary to carry out the work as per best engineering practice and precast coping bedded on top of columns (ref. drawings) | sqm | 192.5
| C.4 | Provision and installation Of Reinforced Cement Concrete (RCC, M25), minimum cement content of 400 kg/cubic meter including Reinforcement (410 MPa) as per details given in drawing, Formworks and all the activities, materials. equipment and manpower necessary to carry out the work as per best engineering practice Provide expansion/contraction joints @ 10 m c/c as per the instructions of the Supervising Engineer (12mm diameter bars and 8mm diameter bars) (ref. drawings) | cum | 19.89
| C.5 | Footings (1000x1000x250)mm RC Pad foundation and underground beam 600X200)mm strip foundation on 50mm thick blinding | cum | 55
| C.6 | Walls 200mm thick, 2400mm high block walling plastered masonery clean plastered as per the plan ingineer (ref. drawings) | sqm | 1068
| C.7 | Columns (250x250)mm and grade beam (200x300)mm Reinforced Concrete | cum | 128.28
Sub-Total
D |  | Concertina Works & Steel Works
| D.1 | Providing and installing three (2) rows or Concenina (450mm diameter, 50 turns, 5 clips) over the | m | 1250
RCC wall including razor wire (double strand traditional twist, 125 gauge, 2 point in 2 rows) for Concertina (ref. drawings)
| D.2 | RCC wall including razor wire (double strand traditional twist, 125 gauge, 2 point in 2 rows) for Concertina
|  | Providing and Installing MS Grills (12mm diameter at 100 mm c/c both ways), Design as per approval of supervising Engineer I .2m x 12m) (ref. drawings) | pcs | 145
| D.3 | Painting works, with approved PLAN colours inside out | sqm | 1680
Sub-Total
| E | Mobilization & Demobilization
| E.1 | The mobilization shall include all activities and associated costs for the transportation/installation o all necessary plant, equipmene general supplies and personnel to the site, | item | 1
| E.2 | Dismantling and transporting plant, equipment and unused supplies, site facilities from the specific location al the end the roject. | Item | 1
Sub-Total
Grand Total