Baseline Terms of Reference

Project: Addressing violence against women and girls as a catalyst for Peace

Location: South Sudan: Wau County (Western Bahr el-Ghazal State) and Pariang County (Unity State)

# Donor: Germany Ministry of Foreign Affairs

Partners: CARE International in South Sudan and Ujamaa Africa Women Empowerment Organization

Contents

Introduction	1

Baseline Summary	1

Project profile	2

Purpose and Objectives	3

Consultant Scope of Works	3

Methodology	3

Approach	3

Sampling	4

Data Sources	4

Data Collection	4

Data Analysis	4

Data Quality Issues	5

Communication of Findings/Reflection	5

Baseline Products/Deliverables	5

Management of the Consultant	5

Data analysis	6

Lessons Learned	6

Limitations	6

Consultant Competency	6

Logistics	6

Payment Terms and Conditions	7

Additional Information	7

Ethical Considerations, Confidentiality and Proprietary Interests.	7

Baseline Report layout	7

# Introduction

# Addressing violence against women and girls as a catalyst for Peace is a two-year project that seeks to promote gender responsive stabilization and recovery of conflict affected women, men, girls and boys in Wau and Pariang.  The Project will specifically support communities to identify and take action against structural causes of gender inequality which promotes conflict and violent notions of masculinity and normalizes the violence. It will also focus on addressing the conflict- related gender-based violence against men and women through improving their access to multi-sectoral GBV services. To achieve sustainable peace an inclusive decision-making process will be promoted where women’s participation and leadership will be strengthened. Through these interconnected outcomes, communities will be able to identify potential solutions for violent conflict thus contributing to attainment of sustainable peace at local and community level, which corresponds with the German foreign policy agenda for South Sudan with its focus on crisis prevention, stabilization and peace-building leading to more sustainable development with a specific focus on women.

# The proposed intervention will target approximately 50,000 women and girls, men and boys, government officials and key community leaders, women leaders, policy makers and civil society organizations. CARE aims to support and enhance the skills and capacity of women’s grassroots organizations and women’s networks and associations and key government institutions so that all can unleash their full potential in peace building, GBV prevention and Response including advocacy skills. CARE will conduct mapping and gap analysis of existing local women structures and networks, provide training to women's associations or networks around capacity development, advocacy and influencing dialogue, gender-based violence and leadership. By enhancing the capacity of women’s associations and networks in Pariang and Wau this should also contribute to sustainability.

The Terms of Reference has been developed to attract interest from consultants to undertake a baseline. This baseline is being undertaken with funding from German MoFA and will be conducted to determine pre-project conditions from which a comparison can be made and also for the purpose of informing the Project Implementation Plan, monitoring progress, evaluating performance, contributing to learning and research.

## Baseline Summary

| Project Name | Addressing violence against women and girls as a catalyst for Peace |
| --- | --- |
| Projects/ Sectors | GBV/Protection, Women Economic Empowerment |
| Projects Coverage | Wau County (Western Bahr el-Ghazal State) and Pariang County (Unity State) |
| Survey Type: | Baseline |
| Survey Purpose: | - To establish the current status of project indicators. This will serve as a basis for setting targets and measuring milestones on outcomes. - To assess and document new knowledge, context analysis and relevant harmful gender social norms which promote conflict and militarized notion of masculinity and normalizes the violence into positive norms that promote peace and gender equality - To map and document information related to availability and access to GBV services and support especially vulnerable women, children and survivors of GBV against men and women |
| Proposed data collection methodology: | Qualitative and quantitative methods in gathering information from both primary and secondary data sources. - Household surveys (remote and face to face) - Focus Group Discussions (To be conducted ensuring COVID-19 guidelines) - Key Informant Interviews - Review of secondary data |
| Proposed start and end dates for baseline study: | 01-February- 2021 |
| Final baseline Survey report submission date: | 01-March-2021 |

## Project profile

| Title | Addressing violence against women and girls as a catalyst for Peace |
| --- | --- |
| Geographic area(s) | Wau County (Western Bahr el-Ghazal State) and Pariang County (Unity State) |
| Project objectives and relevant indicators | - Project aim (outcome/output): Which concrete change to the current situation is the project intended to bring about? Overall Project Objective: To promote gender-transformative stabilization and recovery of conflict-affected women, men, boys and girls in Wau and Pariang Project Specific Objectives: - Communities transform harmful gender social norms which promote conflict and militarized notion of masculinity and normalizes the violence into positive norms that promote peace and gender equality - Targeted communities have increased availability and access to GBV services and support especially vulnerable women, children and survivors of GBV against men and women - Women’s participation in, and influence on local level peace building processes (reconciliation, conflict resolution and dialogues) and decision-making is strengthened |
| Project Duration | 1. December 2020 - 30. November 2022 |
| Total Project Budget | 2,400,000 Euro |

## Purpose and Objectives

The baseline survey is an inception into project monitoring of project outcomes from start, throughout the project life cycle. The baseline for this project has six objectives:

- To establish the current status of project indicators. This will serve as a basis for setting targets and measuring milestones on outcomes.

- To assess and document new knowledge, context analysis and relevant harmful gender social norms which promote conflict and militarized notion of masculinity and normalizes the violence into positive norms that promote peace and gender equality

- To map and document information related to availability and access to GBV services and support especially vulnerable women, children and survivors of GBV against men and women

- To explore the role of women in, and influence on local level peace building processes (reconciliation, conflict resolution and dialogues) and decision-making.

- To understand and document the challenges in regards to women’s participation in, and influence on local level peace building processes (reconciliation, conflict resolution and dialogues) and decision-making.

## Consultant Scope of Works

The consortium lead, CARE South Sudan will facilitate the process to identify a competent consultant to conduct the baseline in consultation with Ujamaa Africa Women Empowerment Organization. As part of the negotiation process, CARE will ensure that the consultant understands and agrees to the assignment, including the baseline scope, purpose, objectives and methodology.  This negotiation includes flexibility to cater for any changes that may arise in the context due to COVID-19, conflict or any other unforeseen changes.

The consultant will design all the relevant data collection techniques, protocols and tools.  The Project Manager, Gender & Protection Advisor, MEAL Coordinator will review the tools and techniques and give feedback prior to the actual baseline measurement. The consultant should remain aware of the changes in the context that could impede the baseline. This assignment should be completed within a maximum of 22 days from inception. Hence, the consultant will:

- Prepare an inception report and hold inception meetings with CARE international in South Sudan and Ujamaa Africa Women Empowerment Organization.

- Develop a simple yet comprehensive baseline design and survey matrix describing type and data to be collected, techniques and relevant tools for each indicator.

- Conduct GBV service mapping.

- Define sampling method, sampling size and targeted respondents

- Review existing literature on the state of GBV, gender roles, norms and laws, women economic empowerment in South Sudan, including, but not limited to German MOFA S03 Office.

## Methodology

### Approach

The consultant will design/use a mixed baseline approach which integrates qualitative and quantitative data collection techniques, tools.

- Quantitative: It is important to be able to acquire data that permits the consortium to compare changes over time in different locations (such as counties) as per the indicators. Household surveys will be conducted to measure the selected indicators. This data should be collected either through face to face interactions.

- Qualitative: Cognizant of COVID-19, the consultant is expected to conduct Focus Group Discussions (FGDs), Key-Informant Interviews (KIIs) while ensuring safety for all participants. Findings from this technique will be used to refine questions raised through the thematic reviews.

### Sampling

The consultant will implement a sampling procedure which is representative of the consortium life of project target population. It is important that the baseline achieves a statistically acceptable sample size for the respective project participant categories.

The consultant will develop, and abide to the approved sampling methodology. Where sampling strategy is changed for whatsoever reason, the consultant is expected to recompute to achieve representative samples with a resubmitted sampling protocol. Therefore, clear and unambiguous proposal on sampling methodology and sample size is expected from the consultant. Sampling method should attain representative and generalizable results for all project participant categories.

### Data Sources

The baseline measurement considers both primary and secondary data sources.

Primary data sources include, but are not limited to:

- female and male (25 years and above) community members

- female and male youth (18 – 25 years)

- female and male community leaders

- Government representatives at state or county level or both?

- Women’s rights organizations

The secondary data sources include but are not limited to studies from South Sudan’s GBV Sub-Cluster, FSL Sub-Cluster, UNFPA, UN Women, FAO, WFP, German MoFA, IPC latest findings and other bilateral donors, project documents. The consultant is expected to undertake review of existing documents using appropriate document review tools and methods.

### Data Collection

The consultant will be responsible to develop data collection tools such as: questionnaires, FGD, KII guides, and observation tools to capture data from the respondents above. Enumerators will be recruited by CARE and trained by the consultant to collect data during household surveys, FGDs and KIIs.  Cognizant of the changing context, data will be captured electronically to expedite the data collection process, minimize data entry errors and improve overall data quality. The COVID-19 pandemic may greatly impede grouped face to face data collection. Hence, the consultant is expected to design a safety protocol for achieving data collection cognizant of Government of South Sudan COVID-19 country SOPs.

### Data Analysis

The consultant should adopt an iterative data analysis approach. This approach allows for prompt data validation as enumerators collect data. Hence, the consultant will develop a data analysis plan. Analysis should integrate findings from the different sources of data. The consultant should corroborate, and triangulate data from different primary data sources.  Depending on access to the country and within the country, the consultant should factor in remote analysis and presentation of findings and sharing of documents in collaborative forums. A complete set of tools and procedures for summarizing and analyzing qualitative data needs to be made available.

### Data Quality Issues

The designed data collection techniques, Quality of data should not be compromised and maximum care should be taken to avoid or at least minimize errors at all stages of the baseline measurement process. Some techniques such as, but not limited to, the following will be applied:

- Before data collection: Pilot testing the data, collection tool will be required in order to verify the reliability and validity of the tool. This includes for both face to face and remote approaches.

- During field data collection: For household surveys, data entry will be on the spot using an electronic questionnaire. Monitoring enumerators for accuracy in doing the interview and in capturing data will be necessary. Checking through all completed responses (on a daily basis) to ensure any mistakes or inconsistencies are corrected on time will add value to the quality of data.

- Data analysis: Perform iterative data analysis which involves continuously analyzing key variables as part of data quality checks using various methods such as: frequencies or cross-tabulations or any forms of regressions

### Communication of Findings/Reflection

Baseline findings will be validated by the community through a validation workshop. Once the validation is completed then the final report will be produced.

### Baseline Products/Deliverables

There will key deliverables of this process:

- An inception report clearly outlining the approach, indicators, methodology and tools Include an annex highlighting how COVID-19 safeguards will be achieved

- Final survey tools and inclusive and gender sensitive sampling design

- Enumerator training, tool pre- testing and data collection

- A comprehensive and well-organized final baseline report in electronic version word and PDF based in the template structure in annex below. (Not more than 30 pages)

- Supporting files, original and cleaned datasets, statistical output files, photos, etc.

- Fact sheet or abstract and power point presentations to be used for dissemination of results to stakeholders

### Management of the Consultant

CARE will support the consultant remotely throughout the baseline. Whenever the consultant is identified, the consultant will work with the Project Manager and Area Managers. The team will commence the inception process to:

- Review of baseline protocols, sampling design, data collection plan, COVID-19 risk reduction plan.

- Finalize tools and approve final plan prior to commencing data collection

- Providing technical support and oversight during data collection process

### Data analysis

- Support data validation through data reviews to identify outliers, clean the dataset, create new variables in advance of analysis by local consultant.

- Support to focus the analysis on concepts/ theories upon which the project is designed on.

- Writing up technical report on baseline data that includes conclusions in key areas or risk and areas of intervention focus.

### Lessons Learned

The lessons learnt through the entire baseline shall be documented and shared with the Project team and CARE quality department so that they may be taken into consideration for future studies. The documentation of these lessons will be vital for reflection, growth and continued improvement.

### Limitations

This baseline survey will be undertaken with some limitations.  These may include:

- COVID-19 pandemic: Guidelines and restrictions may undermine the extent to which sample sizes and limit optimization of selected data collection approach such as FGDs.

- Security: Given the current restrictions in the country, the baseline measurement may be affected by the volatile security condition in some areas.

- Travel Schedules: International and domestic travel between states is mostly by air using UN Flights. In addition, travel schedule may change due to flight cancellation and other technical issues.

- Statistics: Country demographics may not be readily up-to date hence the consultant may have to undertake preliminary data additional data corroboration

### Consultant Competency

A minimum of 5 years or more experience, with the following expertise, experiences and competency

- Proven experience analyzing and understanding of gender dynamics in fragile states

- At least a Master’s Degree qualification in any of the following areas: Gender, Protection, Social Sciences, Development Studies, research or similar qualifications

- Experience undertaking similar studies in South Sudan

- Understanding of Gender, food security and livelihoods dynamics in South Sudan

- Experience leading assessments, feasibility studies or evaluations

- Full understanding on cluster and humanitarian architecture in particular of the Global Protection Cluster and GBV Coordination.

- Excellent analytical, interpersonal, communication and reporting skills

- Knowledge and experience in gender and women’s rights issues

- Excellent command of written and spoken English

### Logistics

Air tickets, Q14, airport pickup and drop off, ground transport and accommodation while in Juba and field locations will be provided. Whereas visas are obtainable on arrival at Juba international airport, travellers are advised to obtain visas in countries where they reside. An introduction letter may be provided on request to support processing of visas.  of payment.

### Payment Terms and Conditions

Payment will be effected as follows; First installment (30%) of the total cost on submission and acceptance of inception report. Final payment (70%) upon completion and approval of the final report. Additional information on payment terms and conditions will be included in the contract.

### Additional Information

- Consultants shall abide to WHO and Government of South Sudan COVID-19 SOPs.

- Consultants shall be required to sign and abide to CARE Safeguarding Policy (which includes prevention of sexual exploitation and abuse, and behavior protocols)

- Consultants shall abide to EU beneficiary data privacy/management policies

### Ethical Considerations, Confidentiality and Proprietary Interests.

- The Consultancy Firm holder needs to apply standard ethical principles during the course of the assignment. Some of these must deal with confidentiality of interviewee statements when necessary, refraining from making judgmental remarks about stakeholders.

- The incumbent shall not either during the term or after termination of the assignment, disclose any proprietary or confidential information related to the service without prior written consent by the contracting authority. Proprietary interests on all materials and documents prepared by the contract holder under this assignment shall become and remain properties of CARE.

### Baseline Report layout

CARE South Sudan will discuss with the successful consultant (s), the content and length of the final report. However, below is a suggested outline for the report.

  - Cover page (1 page)

  - Table of Contents (1 page)

  - Acknowledgements (1 page)

  - Glossary (1 page)

  - Introduction (1 page)

  - Description of Project (1 - 2pages)

  - Executive summary (2 Pages)

  - Baseline introduction/Background/relevant context information (max 2 pages)

  - Limitations of the study

  - Methodology (max 1 pages)

  - Findings (max 10 pages)

  - Summary table of indicator baseline results.

  - Conclusion and recommendations (max 3 pages)

  - Lessons learnt from the baseline process (max 1 pages)

  - Appendices (to include copies of all tools, list of enumerators, survey timeline including all KII and FGD participants and discussion transcripts (as many pages as necessary- please reference the annexes in the report, but include them in a zip file as separate document

Submission.

If you qualify please send your CV, and Technical and financial proposals detailing survey methodology, work plan, budget and sample reports. The Technical proposal with budget and CV should be sent to Sunita.Maharjan@care.org, Richard.Matale@care.org Malish.John@care.org and Patrick.andama@care.org

Deadline for expression of interest is on 15th February 2021 before 4PM.