## BOQs
BOQ for Rehabilitation of 2 Hand Washing Facilities and 3 Rain Water Harvesting Systems, constructon of 1 water drinking point and 1 hand washing facility, extension of pipe water distribution line in Kabu Nursery and Primary School
S/No | Description | Unit | Quantity | Rate (USD) | Amount (USD)
1. Mobilization and demobilization
1.1 | Pre-construction, cleaning, mobilization and demobilization from the site | L.S | 1 | 0 | 0
| Sub-Total: 1 |  |  |  | 0
2. Construction of 1 Drinking water point
2.1 | Remove the top soil at a depth of 35cm and excavate the strip foundation for the hand washing facilities including it manaholes. | Cu.m | 18 | 0 | 0
2.2 | Cast a 10cm thick concrete 1:3:6 for th basement of the handwashing facilities and manholes | Cu.m | 2.4 | 0 | 0
2.3 | Using well burnt red brick of 20 cm wall thickness beded with cement sand mortar of 1:3 ratio, construct the drinking water points according the the attached drawing including all of it grease traps and manholes | Sq.m | 20 | 0 | 0
2.4 | Provide and install 3/4" PPR pipe to be connected to 4 taps and 1 control flange valve and use 4" UPVC pipe to direct to soak way pit through an installed Washing trap | M | 14 | 0 | 0
2.5 | Plaster smoothly the constructed wall surfaces of the hand washing facility,grease traps, and manhole using 1:2 cement sand mortar | Cu.m | 20 | 0 | 0
2.6 | Provide and install 4 taps and at the constructed sink and direct the gray water to the soakway pit through the grease trap | pcs | 10 | 0 | 0
| Sub-Total: 2 |  |  |  | 0
_
3.1 | Remove the top soil and excavate 35cm for a strip foundation and forv handweashing facilities, manaholes and grey water storage tank and soakpit follow the design on the plan | Cu.m | 34 | 0 | 0
3.2 | Cast a 10cm thick concrete 1:3:6 for the basement of the water point inlcuding the manholes, grease trap and for the under ground grey water storage tank | Cu.m | 3 | 0 | 0
3.3 | Using well burnt red brick of 20 cm wall thickness beded with cement sand mortar of 1:3 ratio, construct the handwahing facilities according the the attached drawing including all of its, under grey water ground storage tank, grease traps and manholes | Sq.m | 42 | 0 | 0
3.4 | Provide and install 3/4" PPR pipe to be connected to 10taps and 1 control flange valve and use 4" UPVC pipe to direct togrey water tank then to soak way pit through an installed Washing trap | m | 40 | 0 | 0
3.5 | Cast a reinforced concrete 10cm thick in U-shaped slab for the handwashing facility using Y12 @10cm C/C as well as for the gound grey water storage tank top slab, grease trap manholes. | Cu.m | 3.4 | 0 | 0
3.6 | Plaster smoothly the constructed wall surfaces of the drinking water taps stands,grease traps, manholes and grey water storage tank slab using 1:2 cement sand ratio. | Sq.m | 20 | 0 | 0
3.7 | Provide and install 10 taps and at the constructed handwashing facility and direct the gray water to the soakway pit through the grease trap | pcs | 22 | 0 | 0
| Sub-Total: 3 |  |  |  | 0
4. Rehabilitation of 2 Hand Washing Facilities (HWFs)
4.1 | Replace all the taps for HWFs at the school latrine and ensure each HWF has a floor trap and UPVC pipe for grey water and ensure proper connection of pipe from Rain Water Harvesting Systems and provide and install a manhole cover for the girls latrine block and the gutter are properly fitted | L.S | 1 | 0 | 0
| Sub-Total: 4 |  |  |  | 0
6. Pipe extension
6.1 | Supply and installation of (HDPE flexible) PE 100 pipe OD63 PN10 wall thicks 3mm (1.0)as main distribution line with a value at the joint which extents the pipe to the Handwashing facilites with all neccessay requirements at an adverage depth of 50cm | m | 220 | 0 | 0
| Sub-Total: 6 |  |  |  | 0
| GRAND TOTAL |  |  |  | 0